## Start Here
Delifast — Production Configuration
A step-by-step checklist for taking the backend, dashboards, and mobile app live.
How to use this workbook
Tab | What it's for
Accounts & Costs | Every account you need to open before you start, with cost and purpose
DNS Records | The exact subdomains to point at your hosting provider
Environment Variables | The exact settings to enter in your backend host's dashboard
Deploy Steps | In-order steps to get the backend, dashboards, and first admin live
Go-Live Checklist | Tick each box before you announce launch
iOS App Store Q&A | Every question Apple's submission form asks, in plain language, with a ready answer
Google Play Q&A | Every question Google's submission form asks, in plain language, with a ready answer

## Accounts & Costs
# | Account | Cost | What it's for | Sign up at
1 | Hosting provider (backend) | Free tier, ~$7–25/mo for always-on | Runs your API server 24/7 | render.com or railway.app or fly.io
2 | Managed Postgres database | Free tier, ~$7–15/mo for production | Stores all your data (users, orders, menus) | Same provider as above, or supabase.com / neon.tech
3 | Domain name | ~$10–15/yr | Your web address, e.g. delifast.app | namecheap.com or godaddy.com
4 | Apple Developer Program | $99/yr | Required to publish on the iOS App Store | developer.apple.com/programs
5 | Google Play Console | $25 one-time | Required to publish on Android / Google Play | play.google.com/console/signup
6 | Expo / EAS account | Free to start | Builds your iOS & Android app files | expo.dev
7 | (Later) Payment processor | Varies | Only needed once you accept card payments — Cash on Delivery works without this | paymob.com or fawry.com
8 | (Later) SMS provider | Pay per message | Only needed for SMS order updates / OTP login — optional | twilio.com

## DNS Records
Buy your domain first, then create these records in your domain's DNS settings.
Subdomain | Points to | Used for
api.delifast.app | Your backend host (they give you the exact value to enter) | The Express API — everything talks to this
vendor.delifast.app | Static host for vendor-dashboard build | Restaurant / market owners log in here
admin.delifast.app | Static host for admin-panel build | Your operations team only — keep this private
app.delifast.app (optional) | A marketing/landing page host | Only if you want a public website — not required for the mobile app
Tip: most hosts (Render, Vercel, Netlify) give you a free SSL certificate automatically once DNS points at them. You don't need to buy or install a certificate yourself.

## Environment Variables
Enter these in your hosting provider's "Environment Variables" settings page — never write them into the code.
Variable name | Example value | How to get it
DATABASE_URL | postgresql://user:pass@host:5432/db | Copied exactly from your Postgres provider's dashboard
JWT_SECRET | (long random string) | Run: openssl rand -base64 48 — then paste the result
JWT_EXPIRES_IN | 7d | How long a login lasts before needing to sign in again
NODE_ENV | production | Type exactly this word
ALLOWED_ORIGINS | https://vendor.delifast.app,https://admin.delifast.app | Your two dashboard URLs, separated by a comma, no spaces
PORT | (leave blank) | Most hosts set this automatically
openssl rand -base64 48 is a command you type into Terminal (Mac) or a command prompt. It prints a random password-like string — copy the whole thing into JWT_SECRET.

## Deploy Steps
Step | What to do | Where
1 | Put this whole project on GitHub (a free private repository is fine) | github.com
2 | In your hosting provider, click "New Service" and connect it to that GitHub repo, pointing at the backend folder | Render / Railway / Fly.io dashboard
3 | Paste in all the values from the "Environment Variables" tab | Same dashboard, Environment section
4 | Click Deploy. Wait for it to finish (usually 2–5 minutes) | Same dashboard
5 | Check it worked by visiting https://api.delifast.app/health in your browser — it should show status: ok | Your browser
6 | Create your first admin account by running one command (see note below) | Your computer's terminal
7 | Log in to admin.delifast.app with that account — it will ask you to set up 2-factor login the first time | Browser
8 | Build the two dashboards (vendor + admin) and upload the result to a static host | Terminal, then Vercel/Netlify
9 | Follow the iOS/Android tabs in this workbook to publish the mobile app | Terminal + App Store Connect + Play Console
Step 6 command:
node backend/scripts/create-admin.js "Your Full Name" "+20xxxxxxxxxx" "a-strong-password"

## Go-Live Checklist
Done? | Item
ALLOWED_ORIGINS is set in production (the app won't accept requests without it)
A real, random JWT_SECRET is set (not the placeholder from the example file)
First super-admin created using the script, not any public sign-up form
2-factor login completed for that admin account
Automatic daily database backups turned on with your Postgres provider
Privacy policy published at a real, live web address
Privacy policy reviewed by someone familiar with Egyptian data law (Law No. 151 of 2020)
Decided which cities/areas you deliver to at launch
At least one restaurant/market fully onboarded and tested end-to-end
Test order placed and walked all the way through to "Delivered"

## iOS App Store Q&A
Every question App Store Connect asks when you submit for review or TestFlight testing.
Form asks… | In plain words | Suggested answer for Delifast
App Name | What shows under your icon | Delifast
Subtitle | A short tagline under the name (30 characters max) | Cairo delivery, made simple
Primary Category | Which App Store section it's listed in | Food & Drink
Privacy Policy URL | A live web page explaining what data you collect | https://delifast.app/privacy (publish docs/PRIVACY_POLICY_DRAFT.md there first)
Support URL | A page or email where users can get help | https://delifast.app/support or a support email address
Marketing URL (optional) | A general website link, can be skipped | Leave blank if you don't have one yet
Description | The main text explaining what the app does (4000 characters max) | Order food and groceries from Cairo's best kitchens and markets, delivered fast. Track your order in real time, pay cash on delivery, and reorder favorites in a tap.
Keywords | Search terms, comma-separated (100 characters max) | food delivery, cairo, restaurants, groceries, shawarma, kofta, delivery app
Screenshots | Images of the app on an iPhone screen (required sizes vary by device) | Run: eas build --profile preview, then take screenshots of Home, Menu, Cart, Orders
App Icon (1024×1024) | Your logo, no transparency, no rounded corners (Apple rounds it automatically) | Design a square Delifast "D" badge icon, flat PNG
Age Rating questionnaire | A series of yes/no questions about violence, gambling, etc. | Answer "No" to everything — this is a food delivery app with no mature content
App Privacy ("Nutrition Label") | What data types you collect: Location, Contact Info, User Content, Identifiers | Declare Location (if enabled), Contact Info (phone/name), User Content (orders) — see the notes in docs/PRIVACY_POLICY_DRAFT.md
Data Linked to You? | Is the collected data tied to the person's identity? | Yes — account info and order history are linked to the user
Data Used to Track You? | Is data shared with advertisers/data brokers to track across apps? | No, unless you later add third-party ad tracking
Export Compliance | Does the app use encryption beyond standard HTTPS? | No (standard HTTPS/TLS only) — this usually qualifies for the exemption, confirm the exact wording in the form
Content Rights | Do you own or have rights to everything in the app? | Yes
Advertising Identifier (IDFA) | Does the app use Apple's ad tracking ID? | No, unless you add ads later
TestFlight — Test Information | What testers should know before trying the beta | "This is a beta of the Delifast food delivery app for Cairo. Please use Cash on Delivery for test orders and report any issues."
TestFlight — Beta App Review | A quick review before external testers can install it | Submit the same build info as your main listing; usually approved within 24–48 hours
Build number / Version | Which build testers or reviewers see | Handled automatically by eas build — increments each time
Apple Team ID / App Store Connect App ID | Identifiers found in your Apple Developer account | Look under developer.apple.com → Membership, and appstoreconnect.apple.com → App Information

## Google Play Q&A
Every question Google Play Console asks when you submit for review or internal/closed testing.
Form asks… | In plain words | Suggested answer for Delifast
App name | What shows under your icon | Delifast
Short description | One-line summary (80 characters max) | Cairo food & grocery delivery, made simple.
Full description | The main store listing text (4000 characters max) | Order food and groceries from Cairo's best kitchens and markets, delivered fast. Track your order in real time, pay cash on delivery, and reorder favorites in a tap.
App category | Which Play Store section it's listed in | Food & Drink
Contact details | Email, phone, and/or website shown to users | A support email address, e.g. support@delifast.app
Privacy Policy URL | A live web page explaining what data you collect | https://delifast.app/privacy
App icon (512×512) | Your logo, square PNG | Same icon as iOS, resized
Feature graphic (1024×500) | A banner image shown at the top of your store listing | A simple graphic with the Delifast logo and tagline
Screenshots | At least 2 per supported device type (phone required) | Run: eas build --profile preview, then screenshot Home, Menu, Cart, Orders
Data safety form | What data you collect and why, per category (Location, Personal info, Financial info, etc.) | Declare Location (if enabled), Personal info (name/phone), App activity (order history) — matches your privacy policy
Is data encrypted in transit? | Yes/No question | Yes (standard HTTPS)
Can users request data deletion? | Yes/No — do you support account deletion? | Yes — build an account-deletion request into Profile before answering Yes, or answer honestly if not yet built
Target audience / age | Who is this app for? | 18+ or general audience, food delivery is not directed at children
Content rating questionnaire | IARC questionnaire about violence, gambling, user-generated content, etc. | Answer "No" to everything — no mature content in a food delivery app
Ads declaration | Does the app show ads? | No, unless you add ads later
Government app declaration | Is this an official government app? | No
COVID-19 contact tracing declaration | Is this a contact-tracing app? | No
App access | Do testers/reviewers need a login to see all features? | Provide the test customer login from your seed data, or a real test account
Internal testing track | A quick way to test with a small group before public release | Upload your first build here — add testers by email, no Google review needed
Closed testing track | A wider test group, requires at least 12 testers for 14 days before some new apps can go fully public | Use this after internal testing if Google requires it for a brand-new developer account
Google Play service account key | A JSON credentials file letting eas submit upload automatically | Play Console → Setup → API access → create a service account, download the JSON key